## Hypotheses
source: registers/hypotheses.md · rendered 2026-07-21 (to-table)
ID | Hypothesis | Type | Tags | Status | Born | Source | Test | Confidence
H-001 | The engine can reliably produce native files that are both genuinely editable and genuinely well-designed, at scale | feasibility | — | testing | Step 1 | concept (../1-passport.md#concept) | Step 4: M-edit-fidelity ≥ 90% (fail < 70%) · Step 5: 20 test decks, decision rule set (../5-tactical-plan.md#hypotheses-to-test) · Step 6: F-1+T-1 produce first read (../6-sprint-plan.md#must) | [assumption]
H-002 | Salespeople & marketers are a reachable segment who feel "AI decks look templated" (P1) strongly enough to switch | desirability | — | open | Step 1 | segments/problems (../1-passport.md#problems) | discovery interviews + a demand test (Step 5) | [assumption]
H-003 | "Wrong structure/framing" (P2) is a top pain worth solving, not just styling slides | desirability | — | open | Step 1 | problems (../1-passport.md#problems) | discovery interviews (Step 5) | [assumption]
H-004 | The engine's editable-and-beautiful quality is defensible — hard to replicate cheaply, survives an LLM rebuild. Pressured at Step 2: incumbents (Copilot/Canva) are entering the wedge, so the moat must be the fidelity+design *engine*, not the app | viability | moat | open | Step 1 | value (../1-passport.md#value-defensibility); pressured by ../2-analysis.md#competitor-strategy | observe replication attempts / sustained quality gap (Step 3+) | [assumption]
H-005 | A native, high-fidelity editable-and-designed deck is a real unmet need the lead segment feels and prefers over web-format generation (Gamma's .pptx export flattens 30–40% of slides) — this is the *desire*; whether they'll pay for it is H-009 | desirability | — | testing | Step 2 | opportunity/substitutes (../2-analysis.md#opportunity) | Step 4: M-activation ≥ 30% (fail < 10%) · Step 5: demand probe B-01/B-03, ≥ 10 qualified trials (../5-tactical-plan.md#hypotheses-to-test) · Step 6: A-1 seeds B-01 probe (../6-sprint-plan.md#must) | [assumption]
H-006 | The obtainable market is large enough to build a business on (bottom-up SAM ~$750M; realistic SOM) | viability | — | open | Step 2 | market-sizing (../2-analysis.md#market-sizing) | validate reachable-count + price + adoption assumptions (Step 4) | [assumption]
H-007 | For the beachhead job, "actually-editable + designed native decks" is a strong enough wedge that salespeople & marketers switch (pull beats the "I'll still have to fix it" anxiety + PowerPoint habit) | desirability | — | open | Step 3 | bets (../3-strategy.md#bets); job/forces (../1-passport.md#jtbd) | Step 4: M-wk-retention flattens > 0; demand test (Step 5) | [assumption]
H-008 | A standalone native-fidelity+design engine can stay ahead of incumbents (Copilot/Canva) closing the wedge long enough to build lock-in | viability | moat | open | Step 3 | bets (../3-strategy.md#bets); ../2-analysis.md#opportunity | sustained quality gap + retention once customers exist (pmf) | [assumption]
H-009 | The beachhead will pay a standalone subscription (~$15–25) despite incumbents bundling | viability | — | open | Step 3 | pricing (../3-strategy.md#pricing) | Step 4: WTP ≥ $15/mo (fail < $10); price-talk pilot (Step 5) | [assumption]
H-010 | Sales/marketing communities + product-led virality acquire the beachhead at viable CAC | viability | — | open | Step 3 | channels (../3-strategy.md#channels-expansion) | channel tests with pre-set CAC threshold (Step 5) | [assumption]

## Risks
source: registers/risks.md · rendered 2026-07-21 (to-table)
ID | Risk | Category | Tags | Likelihood | Impact | Mitigation | Owner / Due | Status | Source
R-001 | Gamma is a dominant, profitable leader ($100M ARR, 70M users) — head-on displacement is hard | market | — | H | H | Don't fight head-on — compete on the native-fidelity gap; monitor | ⚙️ founder | accepted (monitored) | Step 2 (../2-analysis.md#niche-risks)
R-002 | Incumbents (Microsoft Copilot in PPT, Canva AI 2.0) bundle native-editable AI generation with distribution — closes our wedge | market | — | H | H | Move fast on the fidelity gap; position sharply on "actually editable"; track their releases | ⚙️ founder · ongoing | mitigating | Step 2 (../2-analysis.md#substitutes)
R-003 | Capable buyers self-build with general LLMs (ChatGPT/Claude) → caps willingness to pay for "just generate slides" | market | — | M | M | — (monitored) | ⚙️ founder | accepted (monitored) | Step 2 (../2-analysis.md#substitutes)
R-004 | Engine quality and COGS depend on third-party LLM providers (cost/availability outside our control) | dependency | — | M | H | Abstract the provider (multi-model); cap M-cogs-per-deck; keep the fidelity engine in-house | ⚙️ eng · ongoing | mitigating | Step 2 (../2-analysis.md#niche-risks)
R-005 | Low entry barrier for "AI slide wrappers" → crowded, fast-moving rivalry | market | — | H | M | — (monitored; the moat is the fidelity engine, not the app) | ⚙️ founder | accepted (monitored) | Step 2 (../2-analysis.md#niche-risks)
R-006 | Manual build / hiring a designer keeps the high-stakes, brand-critical flagship decks | market | — | M | M | — (monitored) | ⚙️ founder | accepted (monitored) | Step 2 (../2-analysis.md#substitutes)
R-007 | The engine never reliably hits native-fidelity + design at scale — the whole strategy rests on one feasibility bet (H-001) | product | execution | M | H | Build the fidelity engine as a thin vertical slice first; gate on M-edit-fidelity ≥ 90% before investing further | ⚙️ founder/eng · next sprint | mitigating | Step 3 (../3-strategy.md#product-risks)
R-008 | The beachhead won't pay standalone vs bundled incumbents (Copilot/Canva at $15–30 bundled) → no viable revenue | financial | — | M | H | Test WTP early (Step 5 pilot) before building billing; don't scale spend until the wedge is validated | ⚙️ founder · Step 5 | open | Step 3 (../3-strategy.md#pricing)
R-009 | Community + product-led virality doesn't materialize → CAC too high to grow | market | execution | M | M | Test inner-ring channels cheaply with a pre-set CAC threshold (H-010) | ⚙️ founder · Step 5 | open | Step 3 (../3-strategy.md#channels-expansion)

## Metric tree
source: registers/metric-tree.md · rendered 2026-07-21 (to-table)
ID | Definition | Unit | Kind | Parent | Instrumentation | Target | Source
M-ns-kept-decks-wk | North Star (⚙️ candidate). Decks generated → exported → kept and edited (used as the real deliverable, not rebuilt by hand) per active deck-maker per week. A redo = the value failed, so this encodes "editable and designed". | count | measured | — (top) | not-instrumented | ⚙️ grow | product events (future)
M-edit-fidelity | THE concept-proving metric. Share of exported slide objects that are natively editable (real shapes/text, not flattened images) — the anti-Gamma metric; proxy for "I don't have to redo it". | % | measured | M-ns-kept-decks-wk | not-instrumented | ⚙️ ≥ 90% | export pipeline (future)
M-activation | Share of new signups who generate AND export a first editable deck ≤ 7d. | % | measured | M-ns-kept-decks-wk | not-instrumented | — to clarify — | product events (future)
M-wk-retention | Share of activated users who return and export another deck the next week. | % | measured | M-ns-kept-decks-wk | not-instrumented | — to clarify — (no cohorts yet) | product events (future)
M-free-paid-conv | Free → paid conversion ≤ 30d (full funnel). | % | measured | M-ns-kept-decks-wk | not-instrumented | — to clarify — | billing (future)
M-cogs-per-deck | LLM inference + render cost per generated deck (COGS). basis: metered = API list price; fact = real spend. | $ | measured | — (guardrail) | not-instrumented | ⚙️ ↓ | LLM/API billing (future)
M-gross-margin | (Revenue − COGS) / Revenue. | % | derived | — (guardrail) | not-instrumented | ⚙️ ≥ 70% | derived (future)

## Strategic plan
source: 4-strategic-plan.md#global-hypotheses · rendered 2026-07-21 (to-table)
H-… | Bet | Metric node (M-…) | Success threshold | Failure threshold | Confidence
H-001 | The engine reliably produces editable+designed native files | M-edit-fidelity | ⚙️ ≥ 90% objects natively editable | < 70% | [assumption]
H-005 | The editable+designed wedge is valued (users keep/edit, don't redo) | M-activation / M-ns-kept-decks-wk | ⚙️ ≥ 30% activate (generate+export+keep) | < 10% | [assumption]
H-007 | The beachhead switches for the wedge | M-wk-retention | ⚙️ retention curve flattens > 0 | decays to 0 | [assumption]
H-009 | Beachhead pays a standalone subscription | (WTP → M-free-paid-conv) | ⚙️ WTP ≥ $15/mo in pilot | < $10/mo | [assumption]

## Sprint plan
source: 6-sprint-plan.md#backlog · rendered 2026-07-21 (to-table)
Rank | Direction | Item | Format | Links (H-…/M-…) | Est. | Confidence
1 | back-office | T-2 · Assemble the 20 representative test decks (layouts, charts, images that fairly stress fidelity) — DoD: 20 decks agreed as representative, versioned | Task+DoD | M-edit-fidelity · R-007 | S | [assumption]
2 | back-office | T-3 · Abstract the LLM provider behind one interface (swap without rewrite) — DoD: provider swappable via config; one alt tested | Task+DoD | M-cogs-per-deck · R-004 | M | [assumption]
3 | go-to-market | A-2 · Intent SEO page "fix Gamma PPT export" (B-03) — capture the Gamma-frustrated intent, route to trial | Activity | H-005 / M-activation | M | [assumption]
4 | development | F-2 · Brand-kit intake (upload colors/fonts → applied to export) for the marketer bundle B-02 | Feature | H-007 / M-activation | M | [assumption]
5 | development | F-3 · Chart-fidelity hardening (native editable charts beyond the one type in F-1) | Feature | H-001 / M-edit-fidelity | M | [assumption]